## User Log
Cravings Restaurant Reservation System
Tickets | Day(s) | Duration | Resource | Project Manager: | Gina R. Gutierrez
1. Documentation |  |  |  | Front-end Programmer: | Joyce A. Bersola
1.1 System Flow Chart |  |  |  | Back-end Programmer: | Dominador B. Pilapil Jr.
1.1.1 Group discussion/meeting | 2018-02-10 | 1 hr | Joyce, Gina, Domi, Mara | QA Tester: | Mara Yssel D. Rabadon
1.1.2 Consultation to adviser | 2018-02-10 | 10 mins | Joyce, Gina, Domi, Mara
1.1.3 Create system flowchart | 2018-02-16 | 10 mins | Mara
1.2 Project Story Board | 2018-02-19 | 2 hrs | Gina
1.3 Project Charter | 2018-02-23 | 2 hrs | Mara
1.4 Project Timeline | 2018-02-23 | 3 hrs | Gina
1.5 Create Tickets | 2/10-03/24 | 6 hrs | Gina
1.5.1 Consolidate updates and changes | 2/10-03/24 | 3 hrs | Gina
2. System Requirements
2.1 Download Visual Studio | 2018-02-22 | 4 hrs | Domi
2.2 Download Access Database | 2018-02-22 | 1 hr | Domi
2.3 Familiarize Visual Studio | 2/19-2/24 | 3 hrs | Joyce, Gina, Domi, Mara
2.4 Study C# Programming | 2/26-3/17 | days | Joyce, Gina, Domi, Mara
2.5 Study how to connect to db | 2/26-3/17 | days | Joyce, Gina, Domi, Mara
3. Design
3.1 Create System Logo | 2018-02-26 | 1 hr | Domi
3.2 Create "Home" form
3.2.1 Background image | 2018-03-09 | 5 mins | Joyce
3.2.2 Header | 2018-03-09 | 2 mins | Joyce
3.2.3 Menu | 2018-03-09 | 10 mins | Joyce
3.2.4 Floor Plan | 2018-03-09 | 2 hrs | Joyce
3.2.5 Calendar | 2018-03-09 | 1 min | Joyce
3.2.6 Legend and Status Panel | 2018-03-09 | 1 min | Joyce
3.2.7 Minimize button | 2018-03-09 | 3 mins | Joyce
3.2.8 Exit button | 2018-03-09 | 3 mins | Joyce
3.3 Create "Create a Reservation" form
3.3.1 Labels | 2018-03-09 | 10 mins | Joyce
3.3.2 TextFields | 2018-03-09 | 5 mins | Joyce
3.3.3. Back button | 2018-03-09 | 1 min | Joyce
3.3.4 Clear button | 2018-03-09 | 1 min | Joyce
3.3.5 Next button | 2018-03-09 | 1 min | Joyce
3.2.6 Minimize button | 2018-03-09 | 1 min | Joyce
3.2.7 Exit button | 2018-03-09 | 1 min | Joyce
3.4 Create "Reservation" form
3.4.1 Labels | 2018-03-09 | 1 min | Joyce
3.4.2 TextFields | 2018-03-09 | 1 min | Joyce
3.4.3 Back button | 2018-03-09 | 1 min | Joyce
3.4.4 Confirm button | 2018-03-09 | 1 min | Joyce
3.5 Create "Records" form
3.5.1 Data Grid | 2018-03-09 | 1 min | Joyce
4. Setting Up
4.1 Gather all images | 2018-03-09 | 30 mins | Joyce
4.1.1 Logo | 2018-03-09 | 10 mins | Joyce
4.1.2 Background images | 2018-03-09 | 10 mins | Joyce
4.2 Set variable names
4.2.1 Home form
4.2.1.1 Menu | 2018-03-16 | 1 min | Gina
4.2.1.2 Floor Plan | 2018-03-16 | 1 min | Gina
4.2.1.3 Calendar | 2018-03-16 | 1 min | Gina
4.2.1.4 Textfields | 2018-03-16 | 1 min | Gina
4.2.1.5 Minimize Label | 2018-03-16 | 5 mins | Joyce
4.2.1.6 Exit Label | 2018-03-16 | 5 mins | Joyce
4.2.2 Create form
4.2.2.1 Menu | 2018-03-16 | 1 min | Gina
4.2.2.2 Textfields | 2018-03-19 | 5 mins | Domi
4.2.2.3 Minimize Label | 2018-03-16 | 1 min | Joyce
4.2.2.4 Exit Label | 2018-03-16 | 1 min | Joyce
4.2.3 Reservation form
4.2.3.1 Buttons | 2018-03-16 | 1 min | Gina
4.2.3.2 Textfields | 2018-03-19 | 5 mins | Domi
4.2.3.3 Minimize Label | 2018-03-16 | 1 min | Joyce
4.2.3.4 Exit Label | 2018-03-16 | 1 min | Joyce
4.2.4 Records form
4.2.4.1 Data grid | 2018-03-19 | 5 mins | Domi
4.2.4.2 Minimize Label | 2018-03-16 | 1 min | Joyce
4.2.4.3 Exit Label | 2018-03-16 | 1 min | Joyce
5. Programming
5.1 Home form
5.1.1 Floor Plan | 2018-03-19 | 2 hrs | Mara
5.1.2 Menu | 2018-03-19 | 15 mins | Joyce
5.2 Create form
5.2.1 Input fields | 2018-03-19 | 2 hrs | Mara
5.2.2 Back button | 2018-03-19 | 5 mins | Gina
5.2.3 Clear button | 2018-03-19 | 5 mins | Gina
5.2.4 Next button | 2018-03-19 | 5 mins | Gina
5.2.5 Send input to database | 3/21-3/27 | days | Domi
5.3 Reservation form
5.3.1 Display inputs | 2018-03-19 | 20 mins | Mara
5.3.2 Back button | 2018-03-19 | 35 mins | Mara
5.3.3 Confirm button | 3/21-3/27 | days | Domi
5.4 Records form
5.4.1 Edit data | 3/21-3/27 | days | Domi
5.4.2 Complete data | 3/21-3/27 | days | Domi
5.4.3 Cancel data | 3/21-3/27 | days | Domi
6. Debugging
6.1 Home form | 3/20-3/27 | days | Joyce, Mara
6.2 Create form | 3/20-3/27 | days | Domi, Mara
6.3 Reservation form | 3/20-3/27 | days | Domi, Mara
6.4 Records form | 3/20-3/27 | days | Domi, Mara
7. Quality Checking
7.1 Check system flow | 2018-03-24 | 1 hr | Gina, Mara
7.2 Check syntax |  |  | Domi, Mara
7.3 Check logical functionality |  |  | Domi, Mara
7.4 Check system functionality |  |  | Domi, Mara
7.5 Check user friendliness |  |  | Joyce, Mara
8. Finalization of the Project
8.1 Documentation | 2018-03-24 | 5 hrs | Gina, Mara
8.2 System Design | 2018-03-19 | 5 hrs | Gina, Mara, Joyce
8.3 System Code |  |  | Joyce,Gina, Mara, Domi
9. Submission of Project | 2018-03-27 | - | Joyce, Gina, Domi, Mara